## luc swinkels
Luc Swinkels
Introweek ¦ Week 1 (week 8 - 19 februari t/m 23 februari)
Name | Status | Estimated hours | Priority | Due date | Subitems
Bedrijfsreglement lezen | Done | XS: < 1 uur | Unknown
Google Drive map verkennen | Done | XS: < 1 uur | Unknown
Benodigde schooldocumenten verzamelen en ordenen | Done | XS: < 1 uur | Unknown
Handleidingen doorlezen | Done | XS: < 1 uur | Unknown
Start Plan van Aanpak maken | Done | XS: < 1 uur | Unknown
Aanmelden Gmail | Done | XS: < 1 uur | Unknown
Aanmelden Toggl | Done | XS: < 1 uur | Unknown
Aanmelden Slack | Done | XS: < 1 uur | Unknown
Aanmelden Monday | Done | XS: < 1 uur | Unknown
Profielfoto's instellen voor Slack, Monday en Gmail | Done | XS: < 1 uur | Unknown
Designen / maken prototype / testen introopdracht in Figma | Done | L: 8 - 16 uur | Unknown
Ontwikkelen introopdracht UI met Laravel | Done | L: 8 - 16 uur | Unknown
Brainstormen introopdracht | Done | S: 1 - 3 uur | Unknown
Belangrijkste deadlines
Name | Status | Estimated hours | Priority | Due date | Subitems
Beoordelingsgesprek 1 | Done | XS: < 1 uur | Unknown | 2024-03-08
Midterm 360-degrees review | Done | M: 3 - 8 uur | Unknown | 2024-05-14
Beoordelingsgesprek 2 | On hold | XS: < 1 uur | Unknown | 2024-06-14
Portfolio inleveren | Unfinished | XL: > 16 uur | Unknown | 2024-06-18
Eindpresentatie/beoordeling | On hold | M: 3 - 8 uur | Unknown | 2024-06-24
2024-03-08 to 2024-06-24
Sprint 0 - week 2 + 3 (Week 9 & 10 - 26 februari t/m 8 maart)
Name | Status | Estimated hours | Priority | Due date | Subitems
Backlog bespreken met jouw begeleider om een taakverdeling en urenindicatie te maken | Done | XS: < 1 uur | Unknown
Deadlines in kaart brengen en noteren | Done | XS: < 1 uur | Unknown
Versie 1 projectplan maken | Done | M: 3 - 8 uur | Unknown
Opzet portfolio (git repo opzetten / project aanmaken / deployment) | Done | S: 1 - 3 uur | Unknown
Inplannen 1e bedrijfsbezoek (week 3/4) | Done | XS: < 1 uur | Unknown
Portfolio klaarmaken voor content toevoegingen (sanity project fixen) | Done | S: 1 - 3 uur | Unknown
Monday inrichten op basis van projectplan planning | Done | XS: < 1 uur | Unknown
Doorlezen canvas informatie Fontys over stage/portfolio/projectplan | Done | XS: < 1 uur | Unknown
Portfolio stijl/werking fixen & updaten | Done | L: 8 - 16 uur | Unknown
Retrospective template maken | Done | XS: < 1 uur | Unknown
Researchdocument template maken | Done | XS: < 1 uur | Unknown
Research web to pdf voor portfolio content archiveren | Done | XS: < 1 uur | Unknown
Versie 1.2 projectplan maken (verwerken feedback docent) | Done | S: 1 - 3 uur | Unknown
Research welke features zijn er nodig op de b2c webshop | Done | M: 3 - 8 uur | Unknown
MoSCoW model maken voor webshop features | Done | XS: < 1 uur | Unknown
Reading guide portfolio pdf versie opzet maken | Done | XS: < 1 uur | Unknown
Sprint demo template presentatie maken | Done | XS: < 1 uur | Unknown
Portfolio video uploads fixen (sanity) | Done | XS: < 1 uur | Unknown
Portfolio codeblock toevoegen | Done | XS: < 1 uur | Unknown
Research magento problemen | Done | M: 3 - 8 uur | Unknown
Retrospective & sprint demo voorbereiden/houden | Done | XS: < 1 uur | Unknown
Portfolio content updaten met sprint 0 content | Done | M: 3 - 8 uur | Unknown
Sprint 1 - week 4 + 5 (Week 11 & 12 - 11 maart t/m 22 maart)
Name | Status | Estimated hours | Priority | Due date | Subitems
Research webshop technologie mogelijkheden | Done | L: 8 - 16 uur | Unknown
Research technische requirements Masita | Done | M: 3 - 8 uur | Unknown
Research UX & Conversie optimalisatie (design pattern research) | Done | L: 8 - 16 uur | Unknown
Opzet Figma styles voor wireframes | Done | XS: < 1 uur | Unknown
Figma design system base componenten bouwen (buttons, cards, varianten) | Done | M: 3 - 8 uur | Unknown
Design wireframes v1 | Done | M: 3 - 8 uur | Unknown |  | Homepage, Category page, Product page, Add to cart, Link pages together (simple clickable prototype), Cart overview, Template page component (navbar/footer/size)
Subitems | Name | Status | Estimated hours | Priority | Priority
| Template page component (navbar/footer/size) | Done | XS: < 1 uur |  | Unknown
| Homepage | Done | XS: < 1 uur |  | Unknown
| Category page | Done | XS: < 1 uur |  | Unknown
| Product page | Done | XS: < 1 uur |  | Unknown
| Add to cart | Done | XS: < 1 uur |  | Unknown
| Cart overview | Done | XS: < 1 uur |  | Unknown
| Link pages together (simple clickable prototype) | Done | XS: < 1 uur |  | Unknown
Retrospective & sprint demo voorbereiden/houden | Done | XS: < 1 uur | Unknown
Portfolio content updaten met sprint 1 content | Done | S: 1 - 3 uur | Unknown
Sprint 2 - week 6 + 7 (Week 13 & 14 - 25 maart t/m 5 april)
Name | Status | Estimated hours | Priority | Due date | Subitems
Design prototype v1 | Done | XL: > 16 uur | Unknown |  | Product componenten maken, Sectie/grid componenten maken, Homepage maken, Category page maken, Product page maken, Add to cart page maken, Cart overview page maken, Fix placeholder content
Subitems | Name | Status | Estimated hours | Priority | Priority
| Product componenten maken | Done | XS: < 1 uur |  | Unknown
| Sectie/grid componenten maken | Done | XS: < 1 uur |  | Unknown
| Homepage maken | Done | XS: < 1 uur |  | Unknown
| Category page maken | Done | XS: < 1 uur |  | Unknown
| Product page maken | Done | XS: < 1 uur |  | Unknown
| Add to cart page maken | Done | XS: < 1 uur |  | Unknown
| Cart overview page maken | Done | XS: < 1 uur |  | Unknown
| Fix placeholder content | Done | XS: < 1 uur |  | Unknown
Peer review prototype v1 | Done | XS: < 1 uur | Unknown
Design prototype v2 op basis van peer review feedback | Done | XL: > 16 uur | Unknown |  | Verwerken feedback v1 Rik/Ryan, Login page, Register page, Account page (order listing), Search UI, Custom kit builder UI, Order confirmation screen (post checkout), Link prototype, Full order listing page, Recording video maken van v2
Subitems | Name | Status | Estimated hours | Priority | Priority
| Verwerken feedback v1 Rik/Ryan | Done | M: 3 - 8 uur |  | Unknown
| Login page | Done | XS: < 1 uur |  | Unknown
| Register page | Done | XS: < 1 uur |  | Unknown
| Search UI | Done | XS: < 1 uur |  | Unknown
| Custom kit builder UI | Done | S: 1 - 3 uur |  | Unknown
| Account page (order listing) | Done | S: 1 - 3 uur |  | Unknown
| Full order listing page | Done | XS: < 1 uur |  | Unknown
| Order confirmation screen (post checkout) | Done | XS: < 1 uur |  | Unknown
| Link prototype | Done | XS: < 1 uur |  | Unknown
| Recording video maken van v2 | Done | XS: < 1 uur |  | Unknown
Research front-end framework | Done | M: 3 - 8 uur | Unknown
Retrospective & sprint demo voorbereiden/houden | Done | XS: < 1 uur | Unknown
Portfolio content updaten met sprint 2 content / backlog content | Done | M: 3 - 8 uur | Unknown
Sprint 3 - week 8 + 9 (Week 15 & 16 - 8 april t/m 19 april)
Name | Status | Estimated hours | Priority | Due date | Subitems
Opzetten usertesting plan voor prototype v2 | Done | M: 3 - 8 uur | Unknown
Usertesting plan uitvoeren | Done | M: 3 - 8 uur | Unknown
Analyseren usertests | Done | S: 1 - 3 uur | Unknown
Research UI libraries/styling | Done | M: 3 - 8 uur | Unknown
Aanpassingen design doorvoeren op basis van testresultaten (final prototype) | Done | M: 3 - 8 uur | Unknown
Monday inrichten met webshop features op basis van MoSCoW prioriteit | Done | XS: < 1 uur | Unknown
Retrospective & sprint demo voorbereiden/houden | Done | XS: < 1 uur | Unknown
Portfolio content updaten met sprint 3 content | Done | M: 3 - 8 uur | Unknown
Portfolio content componenten fixen (accordion) | Done | S: 1 - 3 uur | Unknown
Sprint 4 - week 10 + 11 (Week 17 & 18 - 22 april t/m 3 mei)
Name | Status | Estimated hours | Priority | Due date | Subitems
Vastleggen technologieën | Done | Needs estimation | Unknown
Opzetten project (git repo, core) | Done | Needs estimation | Unknown
Beginnen development must-haves | Added to backlog | Needs estimation | Unknown |  | As a user, I want to be able to look at an overview of products, As a user, I want to be able to look at a specific product, As a user, I want to be able to choose between different variants of a product, As a user, I want to be able to add a product to my shopping cart, As a user, I want to be able to buy a product, As a user, I want to be able to see Masita’s policies and contact info to inquire about returns or other issues., As a Masita employee, I want to be able to register new products, As a Masita employee, I want to be able to edit products, As a Masita employee, I want to be able to adhere to the current Google cookie laws by implementing a cookie policy, As a developer, I want to be able to have freedom of development and not be dependent on plugins or packages
Subitems | Name | Status | Estimated hours | Priority | Priority
| As a user, I want to be able to look at a specific product | Done | L: 8 - 16 uur | Must have | Must have
| As a user, I want to be able to look at an overview of products | Done | L: 8 - 16 uur | Must have | Must have
| As a user, I want to be able to choose between different variants of a product | Done | Needs estimation | Must have | Must have
| As a user, I want to be able to add a product to my shopping cart | Done | L: 8 - 16 uur | Must have | Must have
| As a user, I want to be able to buy a product | Done | M: 3 - 8 uur | Must have | Must have
| As a user, I want to be able to see Masita’s policies and contact info to inquire about returns or other issues. | Done | S: 1 - 3 uur | Must have | Must have
| As a Masita employee, I want to be able to register new products | Done | XS: < 1 uur | Must have | Must have
| As a Masita employee, I want to be able to edit products | Done | XS: < 1 uur | Must have | Must have
| As a Masita employee, I want to be able to adhere to the current Google cookie laws by implementing a cookie policy | Moved to next sprint/backlog | M: 3 - 8 uur | Must have | Must have
| As a developer, I want to be able to have freedom of development and not be dependent on plugins or packages | Done | XS: < 1 uur | Must have | Must have
Retrospective & sprint demo voorbereiden/houden | Done | XS: < 1 uur | Unknown
Portfolio content updaten met sprint 4 content | Done | S: 1 - 3 uur | Unknown
Sprint 5 - week 12 + 13 (Week 19 & 20 - 6 mei t/m 17 mei)
Name | Status | Estimated hours | Priority | Due date | Subitems
Verder met development must-haves | Done | S: 1 - 3 uur | Unknown |  | As a Masita employee, I want to be able to adhere to the current Google cookie laws by implementing a cookie policy (copy)
Subitems | Name | Status | Estimated hours | Priority | Priority
| As a Masita employee, I want to be able to adhere to the current Google cookie laws by implementing a cookie policy (copy) | Done | S: 1 - 3 uur | Must have | Must have
Beginnen development should-haves | Added to backlog | XL: > 16 uur | Unknown |  | As a user, I want to be able to be able to build my own custom product variant, As a user, I want to be able to create an account, As a user, I want to be able to log in, As a user, I want to be able to see my purchase history, As a user, I want to be able to see the website in different languages, As a user, I want to be able to navigate through the website without having to wait for long amounts of time, As a Masita employee, I want to be able to link products to other channels such as bol.com, As a Masita employee, I want to be able to make basic changes to the content of my website, As a Masita employee, I want to be able to edit tax settings, As a Masita employee, I want to be able to discount products, As a Masita employee, I want to be able to send emails to a mailing list of created users, As a developer, I want to be able to work with modern technologies and infrastructure solutions, As a developer, I want to be able to develop and test the store locally, As a developer, I want to be able to have automatic CI/CD integrations and preview environments, As a developer, I want to have a pleasant development experience and not be dependent on old / non-maintained technologies, As a user, I want to be able to filter through a collection of products
Subitems | Name | Status | Estimated hours | Priority | Priority
| As a user, I want to be able to be able to build my own custom product variant | Done | Needs estimation |  | Should have
| As a user, I want to be able to create an account | Out of scope | Needs estimation |  | Should have
| As a user, I want to be able to log in | Out of scope | Needs estimation |  | Should have
| As a user, I want to be able to see my purchase history | Out of scope | Needs estimation |  | Should have
| As a user, I want to be able to see the website in different languages | Out of scope | Needs estimation |  | Should have
| As a user, I want to be able to navigate through the website without having to wait for long amounts of time | Done | Needs estimation |  | Should have
| As a user, I want to be able to filter through a collection of products | Moved to next sprint/backlog | Needs estimation |  | Should have
| As a Masita employee, I want to be able to link products to other channels such as bol.com | Out of scope | Needs estimation |  | Should have
| As a Masita employee, I want to be able to make basic changes to the content of my website | Moved to next sprint/backlog | Needs estimation |  | Should have
| As a Masita employee, I want to be able to edit tax settings | Done | Needs estimation |  | Should have
| As a Masita employee, I want to be able to discount products | Done | Needs estimation |  | Should have
| As a Masita employee, I want to be able to send emails to a mailing list of created users | Done | Needs estimation |  | Should have
| As a developer, I want to be able to work with modern technologies and infrastructure solutions | Done | Needs estimation |  | Should have
| As a developer, I want to be able to develop and test the store locally | Done | Needs estimation |  | Should have
| As a developer, I want to be able to have automatic CI/CD integrations and preview environments | Done | Needs estimation |  | Should have
| As a developer, I want to have a pleasant development experience and not be dependent on old / non-maintained technologies | Done | Needs estimation |  | Should have
Retrospective & sprint demo voorbereiden/houden | Added to backlog | XS: < 1 uur | Unknown
Portfolio content updaten met sprint 5 content | Added to backlog | S: 1 - 3 uur | Unknown
Sprint 6 - week 14 + 15 (Week 21 & 22 - 20 mei t/m 31 mei)
Name | Status | Estimated hours | Priority | Due date | Subitems
Portfolio content updaten met sprint 6 content | Added to backlog | S: 1 - 3 uur | Unknown
Retrospective & sprint demo voorbereiden/houden | Added to backlog | XS: < 1 uur | Unknown
Tests opzetten voor must-haves | Added to backlog | S: 1 - 3 uur | Unknown
Tests uitvoeren voor must-haves | Added to backlog | S: 1 - 3 uur | Unknown
Sprint 7 - week 16 + 17 (week 23 & 24- 3 juni t/m 14 juni)
Name | Status | Estimated hours | Priority | Due date | Subitems
Portfolio updaten (laatste keer) | On hold | XL: > 16 uur | Unknown | 2024-06-14 | All research documents same format, same font (inter), latest version uploaded as pdf, Updated reading guide both online and local (pdf), All posts have correct learning outcomes on both online and local reading guide, Reflectie leeruitkomst 5 maken en content toevoegen, Content development toevoegen, Archiveren portfolio, Leeruitkomst 1+5 midterm review content toevoegen, Monday board exporteren en toevoegen aan agile methodology, Reading guide hoofd/subvragen conclusies toevoegen, Feedback Luuk/Robin verwerken, Final prototype recording maken en op het einde toevoegen aan portfolio
Subitems | Name | Status | Estimated hours | Priority | Priority
| All research documents same format, same font (inter), latest version uploaded as pdf | Done | XS: < 1 uur |  | Unknown
| Reflectie leeruitkomst 5 maken en content toevoegen | Done | S: 1 - 3 uur |  | Unknown
| Updated reading guide both online and local (pdf) | Done | XS: < 1 uur |  | Unknown
| All posts have correct learning outcomes on both online and local reading guide | Done | XS: < 1 uur |  | Unknown
| Content development toevoegen | Done | S: 1 - 3 uur |  | Unknown
| Leeruitkomst 1+5 midterm review content toevoegen | Done | XS: < 1 uur |  | Unknown
| Monday board exporteren en toevoegen aan agile methodology | Done | XS: < 1 uur |  | Unknown
| Reading guide hoofd/subvragen conclusies toevoegen | Done | XS: < 1 uur |  | Unknown
| Archiveren portfolio | On hold | S: 1 - 3 uur |  | Unknown
| Feedback Luuk/Robin verwerken | On hold | S: 1 - 3 uur |  | Unknown
| Final prototype recording maken en op het einde toevoegen aan portfolio | Working on it | XS: < 1 uur |  | Unknown
Backlog functies afwerken op basis van MoSCoW prioriteit | Working on it | L: 8 - 16 uur | Unknown | 2024-06-14 | As a Masita employee, I want to be able to make basic changes to the content of my website, As a user, I want to be able to filter through a collection of products, As a user, I want to be able to scroll through the content of my website on all devices (side-scroll)
Subitems | Name | Status | Estimated hours | Priority | Priority
| As a Masita employee, I want to be able to make basic changes to the content of my website | On hold | Needs estimation |  | Should have
| As a user, I want to be able to filter through a collection of products | Working on it | M: 3 - 8 uur |  | Should have
| As a user, I want to be able to scroll through the content of my website on all devices (side-scroll) | Done | XS: < 1 uur |  | Unknown
Development could-haves | Done | L: 8 - 16 uur | Unknown | 2024-06-14 | As a developer, I want to be able to work with dynamic and scalable code, As a developer, I want to be able to re-use code snippets or elements for future e-commerce projects outside of this project, As a developer, I want to be able to set up and run proper unit / code tests, As a user, I want to be able to see product reviews
Subitems | Name | Status | Estimated hours | Priority | Priority
| As a user, I want to be able to see product reviews | Out of scope | Needs estimation |  | Unknown
| As a developer, I want to be able to work with dynamic and scalable code | Done | Needs estimation |  | Could have
| As a developer, I want to be able to re-use code snippets or elements for future e-commerce projects outside of this project | Done | Needs estimation |  | Could have
| As a developer, I want to be able to set up and run proper unit / code tests | Out of scope | Needs estimation |  | Could have
Retrospective & sprint demo voorbereiden/houden | Unfinished | XS: < 1 uur | Unknown | 2024-06-14
Retrospective/sprint demo's sprint 5/6 toelichten (ziekte) | Done | XS: < 1 uur | Unknown | 2024-06-14
Adviesrapport maken | Done | S: 1 - 3 uur | Unknown
2024-06-14
Sprint 8 - week 18 + 19 (week 25 & 26 - 17 juni t/m 28 juni)
Name | Status | Estimated hours | Priority | Due date | Subitems
Overdracht documenten en andere benodigdheden | Not started | S: 1 - 3 uur | Unknown | 2024-06-28
Voorbereiden presentatie | Not started | M: 3 - 8 uur | Unknown | 2024-06-28
2024-06-28